## AKABOWL
LNO 2019 Fall Fund Raiser
Deliverable | Owner/s | Status | Target Date | Date Completed | Status
Meet with Brunswick cater- discuss details about food packages | Pam | Pending discussion with vendor on how much pizza would feed 100 people | 2019-03-05
Present to Executive Board | Jackie | Will presetn in Soror Pam's absence | 2019-02-25 | 2019-02-25
Sign contract with Brunswick | Chandra
Create fliers and tickets | Cynthia J./Pam | Soror Cynthia is working on flier and tickets. Tickets will be distributed at the June chapter meeting and fliers will be distributed at the Spring Fund Rsiser. | 2019-04-13
Get price and order 3 trophy's | Pam | Soror Tiffiny checked on the trophies total for trophies is $95.70 | 2019-02-25 | 2019-02-22
Fliers to be handed out at Spring fund raiser event/ and adverstised on e-board | Pam
Distribute tickets and fliers at June chapter meeting | Pam
Pick Up Trophies | Pam |  | 2019-10-01

## Entertainment
LNO 2019 Fall Fund Raiser
Deliverable | Owner/s | Status | Target Date | Date Completed | Status
N/A

## Caterer
LNO 2019 Fall Fund Raiser
Deliverable | Owner/s | Status | Target Date | Date Completed | Status
Order the Strike party Available for parties of 15 or more. Served with unlimited soft drinks. All prices are per person. | Pam | Soror Pam is awaiting on the cater to call her back | 2019-03-05

## Key Contacts
Key Contacts
Soror Pam King | Chair